## Worklog_Tasks&Times
Date | Status | Task | Description/Planning | Task Type | Most suited ILO | Est Hours | Actual Hours | Diff | Evidence link | Task reflection / notes
Week 1
week plan: | (Knowledge modules, Domain research)
2023-09-06 | Done | Max 4 hours tasks | Stakeholder analysis | Research |  | 0.5 | 0.5 |  | https://github.com/BredaUniversityADSAI/ADS-AI/blob/a917ce8b71fecae2e1f2cfeeb5deb988ade60611/docs/Study%20Content/Digital%20Transformation/Stakeholder%20analysis%20.pdf
2023-09-06 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 1) videos + homework quiz | Workshop |  | 2 | 2.25 |  | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-06 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 2) videos + homework quiz | Workshop |  | 2 | 2.5 | 0.5 | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-06 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 3) videos + homework quiz | Workshop |  | 2 | 1.75 | -0.25 | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-06 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 3) peer-graded assignment | Workshop |  | 1 | 0.75 | -0.25 | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-06 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 4) videos + homework quiz | Workshop |  | 1.5 | 0.75 | -0.75 | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-06 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 5) videos + homework quiz | Workshop |  | 2.5 | 2 | -0.5 | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-07 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 6) videos + homework quiz | Workshop |  | 1.75 | 1.75 | 0 | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-07 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 7) videos + homework quiz | Workshop |  | 1 | 1.5 | 0.5 | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-07 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 8) videos + homework quiz | Workshop |  | 0.75 | 1 | 0.25 | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-07 | Done | Max 4 hours tasks | Writing in the Sciences: Stanford (week 8) peer-graded assignment | Workshop |  | 1 | 1 | 0 | https://coursera.org/share/125b046d6c427ead7fecf1b6008e2fca
2023-09-07 | Done | Max 4 hours tasks | Writing in Latex: A Primer | Research |  | 1 | 0.25 |  | https://www.overleaf.com/learn/latex/Tutorials
2023-09-08 | Done | Max 4 hours tasks | Group meeting | Meeting |  | 0.15 | 0.15
2023-09-08 | Done | Max 4 hours tasks | Understanding Research Methods (week 1) videos + peer-graded assignment | Workshop |  | 1 | 0.5 | -0.5 | https://coursera.org/share/ccdd6fd5cfdc8bd5fcee09e3e1878186
2023-09-08 | Done | Max 4 hours tasks | Understanding Research Methods (week 2) videos + peer-graded assignment | Workshop |  | 1.75 | 1 |  | https://coursera.org/share/ccdd6fd5cfdc8bd5fcee09e3e1878187
2023-09-08 | Done | Max 4 hours tasks | Understanding Research Methods (week 3) videos + peer-graded assignment | Workshop |  | 1.75 | 1 |  | https://coursera.org/share/ccdd6fd5cfdc8bd5fcee09e3e1878188
2023-09-08 | Done | Max 4 hours tasks | Understanding Research Methods (week 4) videos + peer-graded assignment | Workshop |  | 1 | 0.75 |  | https://coursera.org/share/ccdd6fd5cfdc8bd5fcee09e3e1878189
2023-09-09 | Done | Max 4 hours tasks | Settin up individual repository and files for the project | Distraction |  | 1 | 1 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/tree/main
2023-09-09 | Done | Max 4 hours tasks | Reflecting in Learninglog | Evidencing |  | 0.5 | 0.5 | 0
|  |  |  | Total Hours |  | 24.15 | 20.9 | -3.25
Week 2
week plan: | (Literature Review,High-level Research Design, Research Questions)
2023-09-11 | Done | Max 4 hours tasks | Setting up research proposal in Overleaf | Workshop |  | 1 | 1 | 0 | https://www.overleaf.com/project/64febc62655d64014b6bca08
2023-09-11 | Done | Max 4 hours tasks | LaTex research | Research |  | 1 | 1.5 | 0.5 | https://www.overleaf.com/learn/latex/Tutorials
2023-09-11 | Done | Max 4 hours tasks | PO meeting | Meeting |  | 0.5 | 0.75 | 0.25
2023-09-11 | Done | Max 4 hours tasks | Conducting research on AI in sustainability and FM | Research |  | 2 | 2.5 | 0.5
2023-09-11 | Done | Max 4 hours tasks | Feedback session | Meeting |  | 0.5 | 0.3 | -0.2
2023-09-11 | Done | Max 4 hours tasks | Conducting research on AI in sustainability and FM | Research |  | 1 | 1.5 | 0.5
2023-09-11 | Done | Max 4 hours tasks | Creating an outline for the Research Proposal | Research |  | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/~%24search%20Proposal%20222667.docx
2023-09-12 | Done | Max 4 hours tasks | Problem Statement | Workshop |  | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/~%24search%20Proposal%20222667.docx
2023-09-12 | Done | Max 4 hours tasks | Generating quantitative and qualitative research questions | Workshop |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/drafts/~%24search%20Proposal%20222667.docx
2023-09-12 | Done | Max 4 hours tasks | Creating a outline for Literature Review | Workshop |  | 0.75 | 0.75 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Literature%20Review.docx
2023-09-12 | Done | Max 4 hours tasks | Gathering sources for Literature Review | Workshop |  | 1 | 1.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Literature%20Review.docx
2023-09-13 | Done | Max 4 hours tasks | Conducting Literature Review: Introduction | Research |  | 1 | 1.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Literature%20Review.docx
2023-09-13 | Done | Max 4 hours tasks | Building preliminary research design - High-level research design | Research |  | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/drafts/Research%20Design.docx
2023-09-13 | Done | Max 4 hours tasks | Updating Learninglog | Planning |  | 0.5 | 0.5 | 0
2023-09-13 | Done | Max 4 hours tasks | Brightspace lecture | Lecture |  | 1 | 1 | 0
2023-09-14 | Done | Max 4 hours tasks | Gathering sources for Literature Review | Research |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Literature%20Review.docx
2023-09-14 | Done | Max 4 hours tasks | Stakeholder analysis | Study |  | 1.5 | 1.75 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Stakeholder%20Analysis.docx
2023-09-14 | Done | Max 4 hours tasks | Setting up LaTex in VS code | Testing |  | 3 | 3 | 0
2023-09-14 | Done | Max 4 hours tasks | Conducting Literature Review: Problem Statement analysis | Workshop |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/drafts/Literature%20Review.docx
2023-09-15 | Done | Max 4 hours tasks | Group meeting | Meeting |  | 0.25 | 0.25 | 0
2023-09-15 | Done | Max 4 hours tasks | Conducting Literature Review: first main statement | Workshop |  | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Literature%20Review.docx
2023-09-16 | Done | Max 4 hours tasks | Conducting Literature Review: second main statement | Workshop |  | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Literature%20Review.docx
2023-09-16 | Done | Max 4 hours tasks | Conducting Literature Review: citing references | Workshop |  | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Literature%20Review.docx
2023-09-16 | Done | Max 4 hours tasks | Conducting Literature Review: Conclusion | Workshop |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Literature%20Review.docx
2023-09-17 | Done | Max 4 hours tasks | Reflecting in Learninglog | Evidencing |  | 0.5 | 0.25 | -0.25
|  |  |  | Total Hours |  | 28.5 | 32.3 | 3.8
Week 3
week plan: | (Qualtrics survey, Data Management Plan)
2023-09-18 | Done | Max 4 hours tasks | Formatting research proposal in Overleaf | Workshop |  | 0.75 | 0.5 | -0.25 | https://www.overleaf.com/project/650f02696a6cedcfc6848d72
2023-09-18 | Done | Max 4 hours tasks | PO meeting | Meeting |  | 1 | 0.5 | -0.5
2023-09-18 | Done | Max 4 hours tasks | Exchange program lecture | Lecture |  | 1 | 1 | 0
2023-09-18 | Done | Max 4 hours tasks | Research methods lecture | Lecture |  | 1 | 1 | 0
2023-09-18 | Done | Max 4 hours tasks | Formatting research proposal in Overleaf | Workshop |  | 1 | 0.75 | -0.25 | https://www.overleaf.com/project/650f02696a6cedcfc6848d72
2023-09-18 | Done | Max 4 hours tasks | Market Research course | Workshop |  | 1 | 1.25 | 0.25 | https://www.linkedin.com/learning/certificates/9a5c1384a37a1ee973319cc034163ec861d0baa53630d098472b96b3e9b0b680
2023-09-18 | Done | Max 4 hours tasks | Academic Research Foundations: Quantitative course | Workshop |  | 1 | 1.25 | 0.25 | https://www.linkedin.com/learning/certificates/88772838a95c9d61c555ba486c71ceacf1e4e0fc17ecb0ec6bbec02a11a891fe
2023-09-19 | Done | Max 4 hours tasks | Updating Learninglog | Planning |  | 0.25 | 0.25
2023-09-20 | Done | Max 4 hours tasks | Conducting stakeholder analysis for facility management | Research |  | 1 | 1.5 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Stakeholder%20Analysis.docx
2023-09-20 | Done | Max 4 hours tasks | Generating question for stakeholders and Qualtrics survey | Workshop |  | 0.5 | 0.5
2023-09-20 | Done | Max 4 hours tasks | Formatting research proposal in Word | Workshop |  | 0.5 | 0.25 |  | https://www.overleaf.com/project/650f02696a6cedcfc6848d72
2023-09-20 | Done | Max 4 hours tasks | Overleaf LaTex formatting lecture | Lecture |  | 1 | 1
2023-09-20 | Done | Max 4 hours tasks | Formatting research proposal from template | Workshop |  | 0.25 | 0.25 |  | https://www.overleaf.com/project/6515bc164595ae022838aa54
2023-09-20 | Done | Max 4 hours tasks | Creating Qualtrics survey for data collection | Workshop |  | 0.5 | 0.25 |  | https://buas.eu.qualtrics.com/survey-builder/SV_2cAdIkeCKetjVHg/edit
2023-09-20 | Done | Max 4 hours tasks | Qualtrics survey lecture | Lecture |  | 1 | 1
2023-09-20 | Done | Max 4 hours tasks | Study on how to conduct qualitative research | Study |  | 2 | 2 |  | https://neurolrespract.biomedcentral.com/articles/10.1186/s42466-020-00059-z
2023-09-20 | Done | Max 4 hours tasks | Citing references using BibTex | Workshop |  | 0.5 | 0.75 |  | https://www.overleaf.com/project/64febc62655d64014b6bca08
2023-09-21 | Done | Max 4 hours tasks | Study on how to write DMP | Research |  | 1 | 0.75 |  | https://www.staff.universiteitleiden.nl/courses/library/how-to-write-a-data-management-plan-dmp
2023-09-22 | Done | Max 4 hours tasks | Group meeting | Meeting |  | 0.5 | 0.25
2023-09-22 | Done | Max 4 hours tasks | Setting up group project in Overleaf: research proposal | Workshop |  | 0.5 | 0.5 |  | https://www.overleaf.com/project/650f02696a6cedcfc6848d72
2023-09-22 | Done | Max 4 hours tasks | Setting up individual project in Overleaf: scientifiv report | Workshop |  | 1 | 0.75 |  | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-23 | Done | Max 4 hours tasks | Integrating LaTex in VS code: installing distribution - TeX Live | Distraction |  | 1 | 3
2023-09-23 | Done | Max 4 hours tasks | Integrating LaTex in VS code: installing distribution - MiKTex | Distraction |  | 0.5 | 2
2023-09-23 | Done | Max 4 hours tasks | Managing deliverables files in GitHub repository and One Drive | Workshop |  | 1 | 1 |  | https://edubuas-my.sharepoint.com/personal/222667_buas_nl/_layouts/15/onedrive.aspx?id=%2Fpersonal%2F222667%5Fbuas%5Fnl%2FDocuments%2FYear%202%2FFAI2%2EP1%2D03%20Project%202A&view=0
2023-09-24 | Done | Max 4 hours tasks | Reflecting in Learninglog | Evidencing |  | 0.5 | 0.5
2023-09-25 | Done | Max 4 hours tasks | Setting up group repository in GitHub | Workshop |  | 0.25 | 0.25 | 0
2023-09-25 | Done | Max 4 hours tasks | Formatting research proposal | Workshop |  | 1 | 1 | 0 | https://www.overleaf.com/project/650f02696a6cedcfc6848d72
2023-09-25 | Done | Max 4 hours tasks | Managing sources for scientific report | Research |  | 0.75 | 0.75 | 0 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-25 | Done | Max 4 hours tasks | Integrating R is VS code | Programming |  | 1 | 0.75 | -0.25
2023-09-26 | Done | Max 4 hours tasks | Conducting research on AI in sustainability and FM | Research |  | 2 | 1.5 | -0.5
2023-09-26 | Done | Max 4 hours tasks | Updating Learninglog | Planning |  | 0.5 | 0.5 | 0
|  |  |  | Total Hours |  | 19.75 | 22.25 | 2.5
Week 4
week plan: | (Scientific Report, Data Collection Procedure, Data Storage Protocal)
2023-09-27 | Done | Max 4 hours tasks | Feedback session | Meeting |  | 0.5 | 0.5 | 0
2023-09-27 | Done | Max 4 hours tasks | Scientific report formatting | Workshop |  | 1 | 1 | 0 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-27 | Done | Max 4 hours tasks | Conducting study for new research questions | Research |  | 2 | 2 | 0
2023-09-27 | Done | Max 4 hours tasks | Writing study design in scientific reoprt | Workshop |  | 2 | 1 | -1 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-28 | Done | Max 4 hours tasks | Creating skeleton for the scientific report | Workshop |  | 1 | 1 | 0 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-27 | Done | Max 4 hours tasks | Writing hypotheses (null and alternative) | Workshop |  | 0.5 | 0.5 | 0 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-27 | Done | Max 4 hours tasks | Conducting research and formulating the problem statement | Research |  | 2 | 2.5 | 0.5 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-27 | Done | Max 4 hours tasks | Writing methods sections and study design | Workshop |  | 2 | 1.75 | -0.25 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-28 | Done | Max 4 hours tasks | Formulating Study Design for the individual project | Workshop |  | 1 | 1 | 0 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-28 | Done | Max 4 hours tasks | Conducting research on campus facilities | Research |  | 3 | 2.5 | -0.5
2023-09-28 | Done | Max 4 hours tasks | Changing research questions in accordance to feedback | Workshop |  | 1 | 0.75 | -0.25 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-28 | Done | Max 4 hours tasks | Writing participants, tools, instuments for the individual project | Workshop |  | 3 | 3 | 0 | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-09-28 | Done | Max 4 hours tasks | Conducting research on Buas facilities | Research |  | 1 | 1.5 | 0.5
2023-09-29 | Done | Max 4 hours tasks | Learninglog update | Planning |  | 0.5 | 0.25 | -0.25
2023-09-29 | Done | Max 4 hours tasks | Group meeing | Meeting |  | 0.5 | 0.5 | 0
2023-09-29 | Done | Max 4 hours tasks | Conducting research on data collection methods, tools, instuments (websites, tutorials, examples) | Research |  | 1 | 1 | 0
2023-09-29 | Done | Max 4 hours tasks | Documenting Data Collection Procedure | Workshop |  | 1 | 2.5 | 1.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/DMP/Data%20Collection%20Procedure.pdf
2023-09-29 | Done | Max 4 hours tasks | Conducting research on campus facilities | Research |  | 1 | 1 | 0
2023-09-30 | Done | Max 4 hours tasks | Conducting research on Data Storage Protocal (websites, tutorials, examples) | Research |  | 2 | 3 | 1
2023-09-30 | Done | Max 4 hours tasks | Documenting Data Storage Protocal | Workshop |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/DMP/Data%20Storage%20Protocol.pdf
2023-09-30 | Done | Max 4 hours tasks | Data Management Plan filling in gaps and sections | Workshop |  | 3 | 4 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/DMP/DMP_BUas_2023.pdf
2023-09-30 | Done | Max 4 hours tasks | DDI metadata standard lecture | Distraction |  | 0.5 | 0.5
2023-09-30 | Done | Max 4 hours tasks | Managing files in individual and group repository | Distraction |  | 0.5 | 0.25 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667
2023-10-01 | Done | Max 4 hours tasks | Setting up R and downloading dependencies | Workshop |  | 1 | 1
2023-10-01 | Done | Max 4 hours tasks | R in RS Studio tutorial | Programming |  | 0.75 | 1 |  | https://www.youtube.com/watch?v=yZ0bV2Afkjc
2023-10-01 | Done | Max 4 hours tasks | Testing R environment and packages | Programming |  | 1 | 2
2023-10-01 | Done | Max 4 hours tasks | Finalizing research questions | Research |  | 1 | 1.5 |  | https://www.overleaf.com/project/650f07b21352b16f41f117f1
2023-10-01 | Done | Max 4 hours tasks | Conducting research for survey questions | Research |  | 3 | 4
2023-10-01 | Done | Max 4 hours tasks | Reconstructing Qualtrics survey in accordance to feedback | Design |  |  |  |  | https://buas.eu.qualtrics.com/survey-builder/SV_ehcFRFA1B311yia/edit
|  |  |  | Total Hours |  | 37.75 | 43.5 | 5.75
Week 5
week plan: | (DataCamp course, Interview Questions, Stakeholder analysis, Study Design)
2023-10-02 | Done | Max 4 hours tasks | Introduction to Statistics DataCamp course | Workshop |  | 4 | 4 | 0 | https://www.datacamp.com/statement-of-accomplishment/course/c6fc47c44acec6b3d1660f00496ef58ebac5d515?raw=1
2023-10-02 | Done | Max 4 hours tasks | Foundations of probability in R DataCamp course | Workshop |  | 4 | 4 | 0 | https://www.datacamp.com/statement-of-accomplishment/course/66acfe9c8ae99f1b69cd2ad35a2673cf3759585d?raw=1
2023-10-02 | Done | Max 4 hours tasks | Hypothesis testing in R DataCamp course | Workshop |  | 4 | 4 | 0
2023-10-02 | Done | Max 4 hours tasks | Sampling in R DataCamp course | Workshop |  | 4 | 4 | 0 | https://www.datacamp.com/statement-of-accomplishment/course/bacdded6a2bb75a2b017965dae26fd9b9ae9e013?raw=1
2023-10-02 | Done | Max 4 hours tasks | Qualitrics survey feedback with mentor | Meeting |  | 0.5 | 0.5 | 0 | https://buas.eu.qualtrics.com/survey-builder/SV_d6gVrdDpWIqjQRE/edit
2023-10-02 | Done | Max 4 hours tasks | Changing research questions in accordance to feedback | Workshop |  | 1 | 1 | 0 | https://www.overleaf.com/project/650f02696a6cedcfc6848d72
2023-10-02 | Done | Max 4 hours tasks | Managing local disk storage | Distraction |  | 1 | 2 | 1
2023-10-02 | Done | Max 4 hours tasks | Generating survey questions | Workshop |  | 2 | 1.75 | -0.25 | https://buas.eu.qualtrics.com/survey-builder/SV_d6gVrdDpWIqjQRE/edit
2023-10-02 | Done | Max 4 hours tasks | Linkin pin meeting | Meeting |  | 1 | 1 | 0
2023-10-02 | Done | Max 4 hours tasks | Qualtrics parent survey lecture | Lecture |  | 1 | 0.75 | -0.25 | https://buas.eu.qualtrics.com/survey-builder/SV_d6gVrdDpWIqjQRE/edit
2023-10-02 | Done | Max 4 hours tasks | Conducting research on likert scale data variables | Study |  | 1 | 0.75 | -0.25
2023-10-02 | Done | Max 4 hours tasks | Generating survey questions for campus facilities | Workshop |  | 1 | 0.75 | -0.25 | https://buas.eu.qualtrics.com/survey-builder/SV_d6gVrdDpWIqjQRE/edit
2023-10-03 | Done | Max 4 hours tasks | Writing likert variables for the codebook | Workshop |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/DMP/Codebook.md
2023-10-03 | Done | Max 4 hours tasks | Designing facility management survey | Design |  | 1 | 1 | 0 | https://buas.eu.qualtrics.com/survey-builder/SV_ehcFRFA1B311yia/edit
2023-10-03 | Done | Max 4 hours tasks | Implementing survey question into the parent survey | Testing |  | 0.5 | 1 | 0.5 | https://buas.eu.qualtrics.com/survey-builder/SV_d6gVrdDpWIqjQRE/edit
2023-10-04 | Done | Max 4 hours tasks | Branching blocks in the Main survey | Design |  | 0.5 | 0.25 | -0.25 | https://buas.eu.qualtrics.com/survey-builder/SV_09FeWfCERTprU1w/edit
2023-10-04 | Done | Max 4 hours tasks | Parent survey lecture | Testing |  | 0.5 | 0.5 | 0 | https://buas.eu.qualtrics.com/survey-builder/SV_09FeWfCERTprU1w/edit
2023-10-04 | Done | Max 4 hours tasks | T-test statistics tutorial | Distraction |  | 1 | 1 | 0
2023-10-04 | Done | Max 4 hours tasks | Introduction to R DataCamp course | Workshop |  | 4 | 4 |  | https://www.datacamp.com/statement-of-accomplishment/course/9f3c974c0b12c2680b413b4b290afb95027ba60f?raw=1
2023-10-04 | Done | Max 4 hours tasks | Intermediate R DataCamp course | Workshop |  | 6 | 6 |  | https://www.datacamp.com/statement-of-accomplishment/course/80ae6f26d5aeefc4807b7ba18c12627d6db72271?raw=1
2023-10-04 | Done | Max 4 hours tasks | Ggplot2 R DataCamp course | Workshop |  | 4 | 4 |  | https://www.datacamp.com/statement-of-accomplishment/course/36dd812893d91f165bcd70aab3bc93452ef35df1?raw=1
2023-10-05 | Done | Max 4 hours tasks | Intermediate Statistics LinkedIn course | Workshop |  | 1.5 | 1 |  | https://www.linkedin.com/learning/statistics-foundations-2
2023-10-05 | Done | Max 4 hours tasks | Advanced Statisrtics LinkIn course | Workshop |  | 1.5 | 1 |  | https://www.linkedin.com/learning/statistics-foundations-3
2023-10-06 | Done | Max 4 hours tasks | SMARTER goals | Planning |  | 2 | 1
2023-10-06 | Done | Max 4 hours tasks | Interview quesitons | Research |  | 3 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/Interview%20questions.docx
2023-10-06 | Done | Max 4 hours tasks | Updating Learninglog and Worklog | Evidencing |  | 1 | 0.75
2023-10-06 | Done | Max 4 hours tasks | Scientific report writing | Workshop |  | 2 | 1 |  | https://www.overleaf.com/project/650f07b21352b16f41f117f1
|  |  |  | Total Hours |  | 54 | 50 | -4
Week 6
week plan: | (Interview Questions, Data Analyses, Scientific Report)
2023-10-09 | Done | Max 4 hours tasks | Documenting interview questions | Workshop |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/data/Interview.docx
2023-10-09 | Done | Max 4 hours tasks | Qualitative methods workshop | Workshop |  | 1 | 0.20
2023-10-09 | Done | Max 4 hours tasks | Feedback session | Meeting |  | 0.5 | 0.75 | 0.25
2023-10-09 | Done | Max 4 hours tasks | Stakeholder analysis document | Research |  | 0.75 | 0.75 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/drafts/Stakeholder%20Analysis.docx
2023-10-10 | Done | Max 4 hours tasks | Data Understanding from survey | Programming |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/analyses/data_preprocessing.ipynb
2023-10-10 | Done | Max 4 hours tasks | Data Cleaning on survey data10.10 ver | Programming |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/analyses/data_preprocessing.ipynb
2023-10-11 | Done | Max 4 hours tasks | Data Cleaning on survey data 11.10 ver | Programming |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/analyses/data_preprocessing.ipynb
2023-10-11 | Done | Max 4 hours tasks | Research on sampling population | Research |  | 0.5 | 1 | 0.5
2023-10-11 | Done | Max 4 hours tasks | Performing EDAs | Programming |  | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/analyses/EDA.ipynb
2023-10-11 | Done | Max 4 hours tasks | Research on ANOVA and t-test for ordinal data | Research |  | 1 | 2 | 1
2023-10-12 | Done | Max 4 hours tasks | Linkin pin meeting | Programming |  | 0.75 | 0.75 | 0
2023-10-12 | Done | Max 4 hours tasks | Performing EDAs on 11.10 survey data ver | Programming |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/analyses/EDA.ipynb
2023-10-13 | Done | Max 4 hours tasks | Data Cleaning on survey data 13.10 ver | Programming |  | 1 | 0.75 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/analyses/data_preprocessing.ipynb
2023-10-13 | Done | Max 4 hours tasks | Data Visualization on facility domain bar chart | Programming |  | 1 | 1.5 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/EDAs_facility.R
2023-10-13 | Done | Max 4 hours tasks | Group meeting | Meeting |  | 0.5 | 0.5
2023-10-13 | Done | Max 4 hours tasks | Formating preprocessing and EDAs from notebook to R script | Programming |  | 1 | 1 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/data_preprocessing.R
2023-10-14 | Done | Max 4 hours tasks | Searching candidates from facility management for qualitative research | Research |  | 0.5 | 0.5
2023-10-14 | Done | Max 4 hours tasks | Trying different testing methods (ANOVA and MANOVA) | Testing |  | 1 | 3 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/testing.R
2023-10-14 | Done | Max 4 hours tasks | Trying linear regresion on different variables | Testing |  | 1 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/lr_analysis.R
2023-10-16 | Done | Max 4 hours tasks | Scientific Report: Introduction | Research |  | 2 | 1.5 |  | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-16 | Done | Max 4 hours tasks | Scientific Report: Literature Review | Research |  | 2 | 1.5 |  | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-16 | Done | Max 4 hours tasks | Analysing survey data and subseting | Programming |  | 1 | 1.5 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/EDAs_domains.R
2023-10-16 | Done | Max 4 hours tasks | Conducting EDAs: Bar chart | Programming |  | 2 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/analyses/EDA.ipynb
2023-10-17 | Done | Max 4 hours tasks | Cleaning survey data | Programming |  | 2 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/data_preprocessing.R
2023-10-17 | Done | Max 4 hours tasks | Rewriting functions for data visualizations | Programming |  | 1 | 1 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/EDAs_domains.R
2023-10-17 | Done | Max 4 hours tasks | Scintific Report: formulating hypotheses | Design |  | 1 | 2 |  | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-17 | Done | Max 4 hours tasks | Conducting different testing methods | Testing |  | 2 | 3 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/CI_calculating.R
2023-10-17 | Done | Max 4 hours tasks | Hypothesis testing reporting: summarizing results | Evidencing |  | 4 | 5 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/drafts/Hypothesis%20testing.docx
2023-10-18 | Done | Max 4 hours tasks | Scientific Report: Research Design | Research |  | 2 | 2 |  | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-18 | Done | Max 4 hours tasks | Scientific Report: Methods - Partiticipants and Materials | Research |  | 1 | 2.5 |  | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-18 | Done | Max 4 hours tasks | Scientific Report: Procedure | Distraction |  | 2 | 3 |  | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-19 | Done | Max 4 hours tasks | Normal Distribution tutorial | Distraction |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/CI_calculating.R
2023-10-19 | Done | Max 4 hours tasks | ILOs updating | Evidencing |  | 1 | 2.5 | 1.5
2023-10-19 | Done | Max 4 hours tasks | Linear regresion: scatter plot | Programming |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/lr_analysis.R
2023-10-20 | Done | Max 4 hours tasks | Density data visualizations: plotting confidentece interval | Programming |  | 1 | 3 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/CI_calculating.R
2023-10-20 | Done | Max 4 hours tasks | Ploting density with different percentages of confidence level (one sampe z-test) | Programming |  | 1 | 3 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/CI_calculating.R
2023-10-20 | Done | Max 4 hours tasks | Scientific Report: formulating hypothesis | Research |  | 0.5 | 0.5 |  | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-20 | Done | Max 4 hours tasks | Research on t-test and z-test methods and plotting | Programming |  | 1 | 2
2023-10-20 | Done | Max 4 hours tasks | Research on power methods | Programming |  | 1 | 1
2023-10-21 | Done | Max 4 hours tasks | Plotting scatter plots with data points noise and residuals distances | Programming |  | 1 | 4 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/lr_analysis.R
2023-10-21 |  | Max 4 hours tasks | [5 empty] | 0
|  |  |  | Total Hours |  | 48.5 | 71.25 | 22.75
Week 7
week plan: | (Scietific report, Policy Paper, Research Proposal)
2023-10-23 | Done | Max 4 hours tasks | Woklog update | Evidencing |  | 0.25 | 0.25 | 0
2023-10-23 | Done | Max 4 hours tasks | Fixing data visualizations | Testing |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/EDAs_domains.R
2023-10-23 | Done | Max 4 hours tasks | Sceintific Report: Data Aggregation section | Workshop |  | 0.75 | 1 | 0.25 | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-23 | Done | Max 4 hours tasks | Sceintific Report: Research Design | Evidencing |  | 0.75 | 1 | 0.25 | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-23 | Done | Max 4 hours tasks | Descriptive analysis: Boxplots | Programming |  | 2 | 1.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/EDAs_domains.R
2023-10-23 | Done | Max 4 hours tasks | Linear regression hypothesis testing lecture | Lecture |  | 2 | 2 | 0 | https://edubuas.sharepoint.com/teams/course8762/_layouts/15/stream.aspx?id=%2Fteams%2Fcourse8762%2FShared%20Documents%2FGeneral%2FRecordings%2FLinear%20Regression%20Tutorial%2D20231023%5F153625%2DMeeting%20Recording%2Emp4&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview
2023-10-24 | Done | Max 4 hours tasks | Backward selection for mulitlinear regression | Testing |  | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/models.R
2023-10-24 | Done | Max 4 hours tasks | Group meeting | Meeting |  | 0.25 | 0.25 | 0
2023-10-24 | Done | Max 4 hours tasks | Plotting qqplot, residualcs vs fitted values and scale-loc plot for mlr | Programming |  | 1 | 1.25 | 0.25 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/models.R
2023-10-24 | Done | Max 4 hours tasks | Formatting the scientific report | Design |  | 0.5 | 0.5 | 0 | https://www.overleaf.com/project/6531109d68e9432ad43489de
2023-10-25 | Done | Max 4 hours tasks | Interview for qualitative research | Meeting |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/Data/interview/Call%20with%20Hardjosoedarmo%2C%20Monieka%20(224644)-20231024_163613-Meeting%20Recording-en-US.docx
2023-10-25 | Done | Max 4 hours tasks | Preprocess the transcript and put it the appendices | Distraction |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/Data/interview/Call%20with%20Hardjosoedarmo%2C%20Monieka%20(224644)-20231024_163613-Meeting%20Recording-en-US.docx
2023-10-25 | Done | Max 4 hours tasks | Descriptive analysis: Barcharts | Programming |  | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/EDAs_facility.R
2023-10-25 | Done | Max 4 hours tasks | Data Visualizations and storytellyinh tecture | Lecture |  | 1 | 1 | 0
2023-10-25 | Done | Max 4 hours tasks | ADSAI course management lecture | Lecture |  | 1 | 1 | 0 | https://edubuas.sharepoint.com/teams/course8762/_layouts/15/stream.aspx?id=%2Fteams%2Fcourse8762%2FShared%20Documents%2FGeneral%2FRecordings%2FFast%2DTrack%20%26%203rd%20Year%20Information%20Session%2D20231025%5F160312%2DMeeting%20Recording%2Emp4&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview
2023-10-25 | Done | Max 4 hours tasks | Scietific Report: Results section | Evidencing |  | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/deliverables/Scientific_Report.pdf
2023-10-26 | Done | Max 4 hours tasks | Fixing plots for t-test | Workshop |  | 3 | 4 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/comparison_analysis.R
2023-10-26 | Done | Max 4 hours tasks | Sceintific Report: Qualitative discussion | Workshop |  | 2 | 4 | 2 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/deliverables/Scientific_Report.pdf
2023-10-26 | Done | Max 4 hours tasks | Summarizing trnascripts in the Appendix section | Workshop |  | 1 | 2 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/deliverables/Scientific_Report.pdf
2023-10-26 | Done | Max 4 hours tasks | Conducting power analysis | Workshop |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/comparison_analysis.R
2023-10-26 | Done | Max 4 hours tasks | Visualizing notmal distrubtions with power | Distraction |  | 1 | 4 | 3 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/scripts/power_plots.R
2023-10-27 | Done | Max 4 hours tasks | Group meeting | Meeting |  | 0.25 | 0.25 |  | https://edubuas-my.sharepoint.com/personal/224180_buas_nl/_layouts/15/stream.aspx?id=%2Fpersonal%2F224180%5Fbuas%5Fnl%2FDocuments%2FRecordings%2FCall%20with%20Team%20Facility%2D20231027%5F100342%2DMeeting%20Recording%2Emp4&ga=1&referrer=StreamWebApp%2EWeb&referrerScenario=AddressBarCopied%2Eview
2023-10-27 | Done | Max 4 hours tasks | Scientific Report: Linear and muliti linear regression analysis | Evidencing |  | 2 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/deliverables/Scientific_Report.pdf
2023-10-27 | Done | Max 4 hours tasks | Scientific Report: Hypothesis testing | Evidencing |  | 2 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/deliverables/Scientific_Report.pdf
2023-10-27 | Done | Max 4 hours tasks | Scientific Report: Reliability and Validity instrument | Workshop |  | 2 | 3 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/deliverables/Scientific_Report.pdf
2023-10-27 | Done | Max 4 hours tasks | Calculationg iter test reliability: Cohen Kappa | Distraction |  | 4 | 4
2023-10-28 | Done | Max 4 hours tasks | Wrapping up scientific report | Workshop |  | 2 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/deliverables/Scientific_Report.pdf
2023-10-28 | Done | Max 4 hours tasks | Writing R script for the group repository | Workshop |  | 1 | 1 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/Data/data_cleaning.R
2023-10-28 | Done | Max 4 hours tasks | Cmpleting ILOs | Evidencing |  | 1 | 1 | 0
2023-10-28 | Done | Max 4 hours tasks | Stakeholder analysis for Policy paper | Workshop |  | 1 | 1 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/Stakeholder%20Analysis-%20Week%201%20%26%202/stakeholder%20analysis.pdf
2023-10-28 | Done | Max 4 hours tasks | Streamlit report testing | Testing |  | 1 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/tree/main/presenatation
|  |  |  | Total Hours |  | 43.25 | 53.5 | 10.25
Week 8
week plan: | (Interactive Report, Policy Advice, Research Proposal)
2023-10-30 | Done | Max 4 hours tasks | Feedback session | Meeting |  | 0.5 | 0.5 | 0
2023-10-30 | Done | Max 4 hours tasks | Research Proposal - Literature Review, Research Design | Workshop |  | 3 | 3 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/Research%20%26%20Policy%20papers/Research%20Proposal/Research%20Proposal.pdf
2023-10-30 | Done | Max 4 hours tasks | Managing respository folders | Planning |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main
2023-10-30 | Done | Max 4 hours tasks | Conducting stakeholder analysis | Workshop |  | 2 | 2 |  | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Stakeholder%20Analysis-%20Week%201%20%26%202
2023-10-30 | Done | Max 4 hours tasks | Formating informed concents | Design |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/DMP/Informent%20Consents
2023-10-30 | Done | Max 4 hours tasks | Research Proposal - Ethical Considerations | Design |  | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/Research%20%26%20Policy%20papers/Research%20Proposal/Research%20Proposal.pdf
2023-10-31 | Done | Max 4 hours tasks | Testing streamlit report for final conference | Testing |  | 2 | 3 | 1 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/Digital%20Presentation/presenatation/report.py
2023-10-31 | Done | Max 4 hours tasks | Converting the rscript plots into python scripts for streamlit | Testing |  | 2 | 2.5 | 0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/tree/main/scripts
2023-10-31 | Done | Max 4 hours tasks | Filling out gaps in ILOs section in Learninglog | Distraction |  | 1 | 1 | 0
2023-10-31 | Done | Max 4 hours tasks | Creating framework for the Policy Advice paper | Workshop |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Policy%20Advice
2023-10-31 | Done | Max 4 hours tasks | Writing Policy Advise paper Research Design section | Workshop |  | 2 | 2 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Policy%20Advice
2023-10-31 | Done | Max 4 hours tasks | Writing Executive Summary in the Policy Advice paper | Workshop |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Policy%20Advice
2023-10-31 | Done | Max 4 hours tasks | Writing Discusion section in the Policy Advice paper | Workshop |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Policy%20Advice
2023-11-01 | Done | Max 4 hours tasks | Adding corrections to the scrintific report | Workshop |  | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/blob/main/deliverables/Scientific_Report.pdf
2023-11-01 | Done | Max 4 hours tasks | Formating R script in the group repository | Programming |  | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/blob/main/Data/Data%20Preprocessing.R
2023-11-01 | Done | Max 4 hours tasks | Wrapping up research proposal | Evidencing |  | 1 | 0.5 | -0.5 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Research%20Proposal
2023-11-01 | Done | Max 4 hours tasks | Updating Learninglog and Worklog | Evidencing |  | 0.75 | 0.75 | 0
2023-11-01 | Done | Max 4 hours tasks | Writing Policy Advice Limitations | Workshop |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Policy%20Advice
2023-11-01 | Done | Max 4 hours tasks | Writing Policy Advice Recommendations | Workshop |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Policy%20Advice
2023-11-01 | Done | Max 4 hours tasks | Writing Policy Advisce Implications | Workshop |  | 1 | 0.75 | -0.25 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Policy%20Advice
2023-11-01 | Done | Max 4 hours tasks | Updating Learninglog and Worklog | Evidencing |  | 0.5 | 0.5 | 0
2023-11-01 | Done | Max 4 hours tasks | Wrapping up Policy Advice paper | Workshop |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Policy%20Advice
2023-11-02 | Done | Max 4 hours tasks | Adding graphs and discussion from the scientific report in the poster | Evidencing |  | 1 | 1 | 0 | https://www.canva.com/design/DAFy9U-2B-Q/u5Gb3oDYl55lWrM0un7l2w/edit?amp%3Butm_campaign=designshare&amp%3Butm_medium=link2&amp%3Butm_source=sharebutton
2023-11-02 | Done | Max 4 hours tasks | Preparing all deliverables for sudmission | Evidencing |  | 1 | 1 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-SimonaDimitrova222667/tree/main/deliverables
2023-11-02 | Done | Max 4 hours tasks | Adding final corrections to the Policy Advice | Workshop |  | 2 | 4 | 2 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/Research%20%26%20Policy%20papers/Policy%20Advice
2023-11-02 | Done | Max 4 hours tasks | Adding graphs and discussion from the scientific report in the Streamlit report | Programming |  | 0.5 | 0.5 | 0 | https://github.com/BredaUniversityADSAI/2023-24a-fai2-adsai-group-team-facility/tree/main/DMP/Informent%20Consents
2023-11-02 | Done | Max 4 hours tasks | Preparing for final presentation discussion, recommendations and results | Study |  | 3 | 3 | 0 | https://www.canva.com/design/DAFy9U-2B-Q/u5Gb3oDYl55lWrM0un7l2w/edit?amp%3Butm_campaign=designshare&amp%3Butm_medium=link2&amp%3Butm_source=sharebutton
2023-11-03 | Done | Max 4 hours tasks | Final conference | Presenting |  | 7 | 7 | 0 | https://www.canva.com/design/DAFy9U-2B-Q/u5Gb3oDYl55lWrM0un7l2w/edit?amp%3Butm_campaign=designshare&amp%3Butm_medium=link2&amp%3Butm_source=sharebutton
2023-11-03 | Done | Max 4 hours tasks | Drinks | Distraction |  | 1 | 1 | 0
|  |  |  | Total Hours |  | 42.25 | 44 | 1.75

## Overview
Learning Objective | W1 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | Total Hours for objective
- | [8 empty] | 0
ILO 1.0 | W1: 0 | 0
ILO 2.0 | [8 empty] | 0
ILO 3.1/3.2 | [8 empty] | 0
ILO 4.1/4.2 | [8 empty] | 0
ILO 5.0 | [8 empty] | 0
ILO 6.0 | [8 empty] | 0
0 | [8 empty] | 0
0 | [8 empty] | 0
TOTAL HOURS PER WEEK | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Use this to plan a high level allocation for all 320 hours you are expected to devote to the course during this block. How do you want to allocate your hours for each week? Why 320 hours? The European Higher Education Framework states that an academic credit is expected to require 25-28 hours to earn. You earn 15 credits per block, so you should be expected to devote 375 hours to accomplish that. CMGT students do fewer hours because the program is more intense.
Use a formula like this to get your data from Worklog sheet : =IFERROR(SUM(FILTER('Worklog_Tasks&Times'!$H$5:$H$14,'Worklog_Tasks&Times'!$F$5:$F$14=$B4)),0)

## Drop-downs
Task Status | Task Type | ILO selection
- | - | -
Planned | Design | ILO 1.0
Unplanned | Meeting | ILO 2.0
Blocked | Programming | ILO 3.1/3.2
In-Progress | Research | ILO 4.1/4.2
Done | Testing | ILO 5.0
Delayed | Workshop | ILO 6.0
Cancelled | Planning
Evidencing
Debugging
Lecture
Study
Unplanned
Distraction
Break